## Business Case
Business Case Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | What qualitative information security benefits does this project/solution bring to the organization? | This includes meeting audit and regulatory requirements. | Business Analysis | 1.4
2 | What quantitative information security benefits does this project/solution bring to the organization? | This includes staff reduction through the use of efficiencies gained by automation. | Business Analysis | 1.4

## Vendor Selection Criteria
Vendor Selection Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | What is the vendor's history? | Ensure the vendor's ability to provide delivery of a successful project while ensuring information security practices are aligned with the organization | Interviews with the vendor, asking colleagues, performing search queries on the Internet | N/A
2 | Has the organization dealt with this vendor before? | Past history predicts future performance; this can indicate what is expected from the organization | Reviewing previous contracts, assessing past project's lessons learned | 1.4, 1.5, 2.1, 2.2, 2.5
3 | Where is the vendor located? | This determines what laws the vendor abides by. | Interviews with the vendor, performing search queries on the Internet | N/A
4 | What partnerships does the vendor have? | Provides insight into the vendor's past encounters with other clients. | Interviews with the vendor, performing search queries on the Internet | N/A
5 | What technology does the vendor use? | Determines potential integration pain points. | Interview with the vendor, Internet search | 1.4, 2.4, 2.5
6 | What features does the vendor offer? | Provides insight into the vendor's capabilities and resourcefulness. | Interviews with the vendor, performing search queries on the Internet | 1.4, 2.4, 2.5
7 | Does the vendor have the ability to detect breaches and questionable data messages? | Indicates the priority the vendor places on information security related issues and the ability to respond when an event occurs | Interviews with the vendor, performing search queries on the Internet | 1.4, 2.2, 2.4, 2.5
8 | Does the vendor's product or solution integrate well or seamlessly with other information security related products? | Indicates to the organization how well the vendor's product or service integrates with the organization's previously implemented product or services. | Interviews with the vendor, performing search queries on the Internet | 1.4, 2.5

## Stakeholder Identification
Stakeholder Identification Checklist
Item | Question | Purpose | CIS Sub-Control
1 | Is a member of the information security team involved? | Will typically bring awareness of organizational goals to the project; assists with leading the risk assessment questionnaire (RAQ) | 1.4, 2.1, 2.5
2 | Are members of impacted solutions included? | Provides insight into their systems and the reasoning why certain designs decisions were previously made. | 1.4, 2.1, 2.5
3 | Is a member of the interface team involved? | Provides a broad view of how the systems integrate with one another. | 1.4, 2.1, 2.5
3 | Is a member of the risk management team involved? | Provides insight into what risk the organization is willing to take. | 1.4, 2.1, 2.5
4 | Is a member of the records information management team involved? | Provides information in how the organization stores information. | 1.4, 2.1, 2.5

## Project Charter
Project Charter Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | How does the project's purpose align with information security principles? | Provides security focused value-add benefits to the project. | Solution review | N/A
2 | What information security criteria and deliverables can be listed to ensure success? | Including network asset inventory ensures that the organization is kept up-to-date with the introduction of new solutions. | Asset review workshop, architecture diagrams | 1.4

## Scope Management
Plan Scope Management Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | Has the server been created? | Fulfills the basic technical requirements of the project. | Creating the server based off of a specification sheet (including additional capacity for logging purposes). | 18.3
2 | Has the server been hardened? | Ensures that the server is robust in the environment. | Following organizational hardening procedures (for example, changing default passwords, closing unneeded ports, and so on). | 18.11
3 | Has the server been tested? | Validates the system is secure and develops a plan of action for those that are not complete. | Vulnerability scans, remediating found issues, providing compensating controls for unchanged items. | 3.1, 3.6, 3.7
3 | Has the server received signoff? | Brings the vendor into the process to ensure functionality and their approval with the system. | Vendor testing | N/A
4 | Are all account types using an approved password complexity structure and contain the correct privileges? | Ensures that the project aligns any account passwords with organization's best practices. | Reviewing accounts by type (administrator, user) and ensuring the policy matches the organization's. Implement role-based access controls for account types. | 4.4, 16.7
5 | Are there any other security features that can be reviewed with the solution? Examples include incorporating multi-factor authentication, using encrypted only channels, and so on. | Ensures that the solution is able to provide long-term success and acceptable maintenance within the organization. | Technical review workgroup | 2.7, 10.1, 14.1, 16.3, 16.5

## Plan Communications
Plan Communications Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | What can I do to ensure that information that I have pertaining to this project is kept secure? | Base communications answering this question to enhance the security posture of the project and organization. | Project kickoff meetings, project meetings, emails, other various communication channels | 17.x

## Plan Risk Management
Plan Risk Management Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | Where is the solution hosted? Is the solution hosted on-premises and supported by the organization? Is the solution hosted off-site? | Determines what security controls are needed for solution. | Risk assessment questionnaire | N/A
2 | What is the data classification for the solution? | Determines what laws govern the data. | Risk assessment questionnaire | N/A
3 | What is the solution's provisioning strategy? | Determines who is responsible for creating accounts for solution. | Risk assessment questionnaire | 16.2
3 | What is the solution's backup and data recovery strategy? | Provides insight into how the solution is able to restore its files in the event of an incident or disaster. | Risk assessment questionnaire | 10.x
4 | Does the vendor need to use external media (USB, CD, or floppy disk) for any reason throughout the life of the project? | Determines what security controls the organization needs to take. | Risk assessment questionnaire | 13.7
5 | Can the vendor provide on-demand audit requests such as the Standards for Attestation Engagement No. 16 (SSAE 16)? | Provides the organization assurances in the event of an audit. | Risk assessment questionnaire | N/A
6 | Is the data that is handled protected at rest and in transit per guidelines outlined in Federal Information Processing (FIPS) 140-2? | Demonstrates that the vendor meets governmental standards. | Risk assessment questionnaire | N/A

## Plan Procurement
Plan Procurement Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | Have the basic requirements of the contract been reviewed? Examples include purpose of the contract, estimated time for effort, security requirements, pricing, conversion (pre/post) strategy, and so on. | Provides the organization the statement of work that is needed to complete the effort. This is important in the event issues arise. | Contract review | N/A
2 | Have other subject matter experts (SMEs) reviewed the contract? | Provides oversight into the project review process. | Contract review workshops | N/A

## Business Associate Agreements
Business Associate Agreement (BAA) Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | What technical, administrative, and physical safeguards is written in the agreement? | Provides the elements outlined in HIPAA's Security Review. | BAA Creation and Review | N/A
2 | Are there limitations pertaining to use and disclosure? | Provides the elements outlined in HIPAA's Privacy Rule. | BAA Creation and Review | N/A
3 | Does the BAA discuss obligations by the Covered Entity? | Provides answers to important questions including but not limited to: (1) providing the organization’s “Notice of Privacy Practices” (NPP); notifying the business associate if individuals change or modification of permission of their PHI; (3) notifying the business associate if there are any restrictions that impact the use or disclosure of the PHI; (4) stating that the business associate should not engage in actions that violate what is outlined in HIPAA/HITECH acts; (5) stating that the business associate is able to rely on any instructions; (6) following the notification breach process in the event of a breach; and (7) any transaction-specific concerns | BAA Creation and Review | N/A
4 | Does the BAA discuss obligations by the Business Associate? | Provides answers to important questions including, but not limited to, the following: (1) providing the organization’s “Notice of Privacy Practices” (NPP); notifying the business associate if individuals change or modification of permission of their PHI; (3) notifying the business associate if there are any restrictions that impact the use or disclosure of the PHI; (4) stating that the business associate should not engage in actions that violate what is outlined in HIPAA/HITECH acts; (5) stating that the business associate is able to rely on any instructions; (6) following the notification breach process in the event of a breach; and (7) any transaction-specific concerns | BAA Creation and Review | N/A

## Project Monitoring
Project Monitoring and Control Checklist
Item | Objective | CIS Sub-Control
1 | Keeping project data secure should be a priority for the project team. | 17.x
2 | Changes to the project need to follow the organization’s change management process. | 14.9
3 | If the project is in collaboration with a vendor, configure scheduled access reviews with the vendor team. | 16.7
4 | Involve project members (including vendors) in information security exercises (such as phishing campaigns). | 17.x

## Project Closure
Project Closure Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | Have you conducted a lesson's learned session? | Strengthens the security posture of future projects. | Lessons Learned | N/A
2 | What is the data classification for the solution? | Determines what laws govern the data. | Risk assessment questionnaire | N/A
3 | What is the solution's provisioning strategy? | Determines who is responsible for creating accounts for solution. | Risk assessment questionnaire | 16.2
3 | What is the solution's backup and data recovery strategy? | Provides insight into how the solution is able to restore its files in the event of an incident or disaster. | Risk assessment questionnaire | 10.x
4 | Does the vendor need to use external media (USB, CD, or floppy disk) for any reason throughout the life of the project? | Determines what security controls the organization needs to take. | Risk assessment questionnaire | 13.7
5 | Can the vendor provide on-demand audit requests such as the Standards for Attestation Engagement No. 16 (SSAE 16)? | Provides the organization assurances in the event of an audit. | Risk assessment questionnaire | N/A
6 | Is the data that is handled protected at rest and in transit per guidelines outlined in Federal Information Processing (FIPS) 140-2? | Demonstrates that the vendor meets governmental standards. | Risk assessment questionnaire | N/A