## ReadMe
Information Security Best Practices While Managing Projects
Author: Dallas Smith Advisor: Rajat Varuni
General Information
This workbook serves as an extension to the paper titled "Information Security Best Practices While Managing Projects." Essentially, this workbook aims at assitsing project managers when working through their projects. By following the items on these checklists, project managers include information security best practices in their efforts. The items on this checklist came from my previous work experience and by conducting in-depth research. I have cited the references for each of the worksheets for items that came from outside sources.
Change Log
Version 1.0 - Created the original workbook. (March 12, 2019)
Version 1.1 - Added the Checklist worksheet. (March 12, 2019)

## Checklist
Business Case Checklist
Question
Does the project or solution bring the organization any qualitative information security benefits?
Does the project or solution bring the organization any quantitative information security benefits?
Vendor Selection Criteria Checklist
Question
What is the vendor's history?
Has the organization dealt with this vendor before?
Where is the vendor located?
What partnerships does the vendor have?
What technology does the vendor use?
What features does the vendor offer?
Does the vendor have the ability to detect breaches?
Does the vendor's product or solution integrate well or seamlessly with other information security related products?
Stakeholder Identification Checklist
Question
Is a member of the information security team involved?
Are members of impacted solutions included?
Is a member of the interface team involved?
Is a member of the risk management team involved?
Is a member of the records information management team involved?
Project Charter Checklist
Question
How does the project's purpose align with information security principles?
What information security criteria and deliverables can be listed to ensure success?
Scope Management Checklist
Question
Has the server been created?
Has the server been hardened?
Has the server been tested?
Has the server received vendor signoff?
Are all account types using an approved password complexity structure and contain the correct privileges?
Are there any other security features that can be reviewed with the solution? Examples include incorporating multi-factor authentication, using encrypted only channels, and so on.
Plan Communications Checklist
Question
What can I do to ensure that information that I have pertaining to this project is kept secure?
Plan Risk Management Checklist
Question
Where is the solution hosted? Is the solution hosted on-premises and supported by the organization? Is the solution hosted off-site?
What is the data classification for the solution?
What is the solution's provisioning strategy?
What is the vendor’s backup and data recovery strategy?
Does the vendor need to use external media (USB, CD, or floppy disk) for any reason throughout the life of the project?
Can the vendor provide on-demand audit requests such as the Standards for Attestation Engagement No. 16 (SSAE 16)?
Is the data protected at rest and in transit per guidelines outlined in Federal Information Processing (FIPS) 140-2?
Plan Procurement Checklist
Question
Have the basic requirements of the contract been reviewed? Examples include the purpose of the agreement, estimated time for effort, security requirements, pricing, conversion (pre/post) strategy, and so on.
Have other subject matter experts (SMEs) reviewed the contract?
Business Associate Agreements Checklist
Question
What are the technical, administrative, and physical safeguards written in the agreement?
Are there limitations about use and disclosure?
Does the BAA discuss obligations by the Covered Entity?
Does the BAA discuss obligations by the Business Associate?
Project Monitoring Checklist
Question
Keeping project data secure should be a priority for the project team.
Changes to the project need to follow the organization’s change management process.
If the project is in collaboration with a vendor, configure scheduled access reviews with the vendor team.
Involve project members (including vendors) in information security exercises (such as phishing campaigns).

## Business Case
Business Case Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | Does the project or solution bring the organization any qualitative information security benefits? | Includes meeting audit and regulatory requirements or fixing security based issues (Nemati, 2008, p. 2649). | Business Analysis | 1.4
2 | Does the project or solution bring the organization any quantitative information security benefits? | Includes gaining cost savings through automation or other security-specific benefits (Purser, 2004, p. 203). | Business Analysis | 1.4
References
Nemati, H. R. (2008). Information Security and Ethics: Concepts, Methodologies, Tools and Applications. Hershey PA: IGI Global.
Purser, S. (2004). A Practical Guide to Managing Information Security. Norwood, MA: Artech House, Inc.

## Vendor Selection Criteria
Vendor Selection Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | What is the vendor's history? | Ensure the vendor's ability to provide delivery of a successful project while ensuring information security practices aligns with the organization. | Interviews with the vendor, asking colleagues, Internet search | N/A
2 | Has the organization dealt with this vendor before? | History predicts future performance; this can indicate expectations from the organization. | Reviewing previous contracts, assessing past project's lessons learned | 1.4, 1.5, 2.1, 2.2, 2.5
3 | Where is the vendor located? | Determines what laws the vendor follows. | Interviews with the vendor, Internet search | N/A
4 | What partnerships does the vendor have (Legelis & O’Brien, 2018)? | Provides another source of credibility to the vendor’s capabilities. | Conversation with the vendor, Internet search | N/A
5 | What technology does the vendor use (Legelis & O’Brien, 2018)? | Determines potential integration issues. | Conversation with the vendor, Internet search | 1.4, 2.4, 2.5
6 | What features does the vendor offer (Legelis & O’Brien, 2018)? | Provides information about additional integration points. | Interviews with the vendor, Internet search | 1.4, 2.4, 2.5
7 | Does the vendor have the ability to detect breaches (Legelis & O’Brien, 2018)? | Indicates the priority the vendor places on information security related issues and the ability to respond when an event occurs. | Interviews with the vendor, Internet search | 1.4, 2.2, 2.4, 2.5
8 | Does the vendor's product or solution integrate well or seamlessly with other information security related products (Legelis & O’Brien, 2018)? | Indicates to the organization how well the vendor's product or service integrates with the organization's previously implemented product or services. | Interviews with the vendor, Internet search | 1.4, 2.5
References
Legelis, K., & O'Brien, L. (2018, December 18). Simplifying the ICS Cyber Security Vendor Selection Process. Retrieved February 19, 2019, from https://www.nozominetworks.com/2018/12/18/blog/simplifying-the-ics-cyber-security-vendor-selection-process/

## Stakeholder Identification
Stakeholder Identification Checklist
Item | Question | Purpose | CIS Sub-Control
1 | Is a member of the information security team involved? | Will typically bring awareness of organizational goals to the project; assists with leading the risk assessment questionnaire (RAQ). | 1.4, 2.1, 2.5
2 | Are members of impacted solutions included? | Ensures the team can discuss all systems and determine the reasoning behind previous design decisions. | 1.4, 2.1, 2.5
3 | Is a member of the interface team involved? | Provides a broad view of how the systems will integrate. | 1.4, 2.1, 2.5
3 | Is a member of the risk management team involved? | Provides insight into what risk the organization is willing to take. | 1.4, 2.1, 2.5
4 | Is a member of the records information management team involved? | Provides information on how the organization stores information. | 1.4, 2.1, 2.5

## Project Charter
Project Charter Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | How does the project's purpose align with information security principles? | Provides security focused value-add benefits to the project. | Solution review | N/A
2 | What information security criteria and deliverables can be listed to ensure success? | Including network asset inventory ensures that the organization is kept up-to-date with the introduction of new solutions. | Asset review workshop, architecture diagrams | 1.4

## Scope Management
Plan Scope Management Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | Has the server been created? | Fulfills the technical requirements of the project. | Building the server based off of a specification sheet (including the capacity for logging purposes). | 18.3
2 | Has the server been hardened? | Ensures that the server is robust in the environment. | Following organizational hardening procedures (for example, changing default passwords, closing unneeded ports, and so on). | 18.11
3 | Has the server been tested? | Validates the system is secure and develops a plan of action for those that are not complete. | Vulnerability scans, remediating found issues, providing compensating controls for unchanged items. | 3.1, 3.6, 3.7
3 | Has the server received vendor signoff? | Brings the vendor into the process to ensure functionality and their approval with the system. | Vendor review | N/A
4 | Are all account types using an approved password complexity structure and contain the correct privileges? | Ensures that the project aligns any account passwords with the organization's best practices. | Reviewing accounts by type (administrator, user) and ensuring the policy matches the organization. Implement role-based access controls for account types. | 4.4, 16.7
5 | Are there any other security features that can be reviewed with the solution? Examples include incorporating multi-factor authentication, using encrypted only channels, and so on. | Ensures that the solution can provide long-term success and acceptable maintenance within the organization. | Technical review workgroup | 2.7, 10.1, 14.1, 16.3, 16.5

## Plan Communications
Plan Communications Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | What can I do to ensure that information that I have pertaining to this project is kept secure? | Base communications answering this question to enhance the security posture of the project and organization. | Project kickoff meetings, project meetings, emails, other various communication channels | 17.x

## Plan Risk Management
Plan Risk Management Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | Where is the solution hosted? Is the solution hosted on-premises and supported by the organization? Is the solution hosted off-site? | Determines what security controls are needed for the solution. | Risk assessment questionnaire | N/A
2 | What is the data classification for the solution? | Determines what laws govern the data (Broad, 2013, pg. 173). | Risk assessment questionnaire | N/A
3 | What is the solution's provisioning strategy? | Determines who is responsible for creating accounts for the solution (Bertino & Takahashit, 2010, p. 30-35). | Risk assessment questionnaire | 16.2
3 | What is the vendor’s backup and data recovery strategy? | Provides insight into how the solution can restore its files in the event of an incident or disaster (Stier, 2015, p. 50). | Risk assessment questionnaire | 10.x
4 | Does the vendor need to use external media (USB, CD, or floppy disk) for any reason throughout the life of the project? | Determines what security controls the organization needs to take (Vladimirov, Michajlowski, & Gavrilenko, 2014, p. 162). | Risk assessment questionnaire | 13.7
5 | Can the vendor provide on-demand audit requests such as the Standards for Attestation Engagement No. 16 (SSAE 16)? | Provides the organization assurances in the event of an audit (Gonsalves, 2011, p. 34). | Risk assessment questionnaire | N/A
6 | Is the data protected at rest and in transit per guidelines outlined in Federal Information Processing (FIPS) 140-2? | Demonstrates that the vendor meets regulatory standards (Bomgar Receives FIPS 140-2 Level 2 Validation, 2014, p. 6). | Risk assessment questionnaire | N/A
References
Bertino, E., & Takahashi, K. (2010). Identity Management: Concepts, Technologies, and Systems. Boston, MA: Artech House, Inc.
Bomgar Receives Fips 140-2 Level 2 Validation. (2014). Computer Security Update, 15(5), 6–7.
Broad, J. (2013). Risk Management Framework: A Lab-Based Approach to Securing Information Systems. Amsterdam: Syngress.
Gonsalves, N. S. (2011). The New Standard. Collector (0010082X), 76(11), 33–37.
Vladimirov, A. A., Michajlowski, A., & Gavrilenko, K. (2014). Assessing Information Security : Strategies, Tactics, Logic and Framework (Vol. Second edition). Ely, Cambridgeshire: IT Governance Publishing

## Plan Procurement
Plan Procurement Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | Have the basic requirements of the contract been reviewed? Examples include the purpose of the agreement, estimated time for effort, security requirements, pricing, conversion (pre/post) strategy, and so on. | Provides the organization the statement of work that is needed to complete the effort; this is important in the event issues arise (Kubitscheck, 2014, p. 54). | Contract review | N/A
2 | Have other subject matter experts (SMEs) reviewed the contract? | Provides oversight into the project review process. | Contract review workshops | N/A
References
Kubitscheck, V. (2014). Integrated Assurance: Risk Governance Beyond Boundaries. Farnham: Routledge.

## Business Associate Agreements
Business Associate Agreement (BAA) Checklist
Item | Question | Purpose | Methods | CIS Sub-Control
1 | What are the technical, administrative, and physical safeguards written in the agreement? | Provides the elements outlined in HIPAA's Security Review (American Dental Association, 2017, p. 109). | BAA Creation and Review | N/A
2 | Are there limitations about use and disclosure? | Provides the elements outlined in HIPAA's Privacy Rule (American Dental Association, 2017, p. 109). | BAA Creation and Review | N/A
3 | Does the BAA discuss obligations by the Covered Entity? | Provides answers to essential questions including but not limited to: (1) providing the organization’s “Notice of Privacy Practices” (NPP); (2) notifying the business associate if individuals change or modification of permission of their PHI; (3) notifying the business associate if there are any restrictions that impact the use or disclosure of the PHI; (4) stating that the business associate should not engage in actions that violate what is outlined in the HIPAA/HITECH acts; (5) indicating that the business associate is able to rely on any instructions; (6) following the notification breach process in the event of a breach; and (7) any transaction-specific concerns (Classen, Fogarty, Mier, 2012, pp. 6-7). | BAA Creation and Review | N/A
4 | Does the BAA discuss obligations by the Business Associate? | Provides answers to essential questions including, but not limited to, the following: (1) providing the organization’s “Notice of Privacy Practices” (NPP); notifying the business associate if individuals change or modification of permission of their PHI; (3) notifying the business associate if there are any restrictions that impact the use or disclosure of the PHI; (4) stating that the business associate should not engage in actions that violate what is outlined in HIPAA/HITECH acts; (5) indicating that the business associate is able to rely on any instructions; (6) following the notification breach process in the event of a breach; and (7) any transaction-specific concerns (Classen, Fogarty, Mier, 2012, pp. 8-72). | BAA Creation and Review | N/A
References
American Dental Association (2017). Managing the Regulatory Environment: Guidelines for Practice Success: Best Practices. Chicago: American Dental Association.
Classen, H. W., Fogarty, M., & Mier, B. (2012). Anatomy of a Business Associate Agreement, Part I. Journal of Health Care Compliance, 14(4), 5–73.
Classen, H. W., Fogarty, M., & Mier, B. (2012). Anatomy of a Business Associate Agreement, Part II. Journal of Health Care Compliance, 14(5), 5–12.

## Project Monitoring
Project Monitoring and Control Checklist
Item | Objective | CIS Sub-Control
1 | Keeping project data secure should be a priority for the project team. | 17.x
2 | Changes to the project need to follow the organization’s change management process. | 14.9
3 | If the project is in collaboration with a vendor, configure scheduled access reviews with the vendor team. | 16.7
4 | Involve project members (including vendors) in information security exercises (such as phishing campaigns). | 17.x